## Estimates for V2
Section	Est	Hrs	Description
TOTAL	115
1.0	37		APP
1.1		8	Show Data Previously Earned for a Project
1.2		5	If ZIP code is entered, auto populate
1.3		2	Integrate ACRA
1.4		8	Add notes to pictures
1.5		5	Error checking on various numbers
1.6		4	Display truck number list
1.7		5	Add status of install option
2.0	41		Server
2.1		6	Deactivate project option
2.2		6	Separate out city & company from entries
2.3		4	Better navigation
2.4		8	Require login
2.5		2	Project/client association
2.6		12	Progress Grid
2,7		3	Entry new column
2.8	37		Work Orders
2.8.1		6	New Screen
2.8.2		16	Import
2.8.3		12	Color coding
2.8.4		3	Data pushed to APP